CPM : Rocks and Robots

Activity Duration Effort Action

A 1day 1hr Decide Game, create rules (completed)

B 2 day 3 hr Create/find/decide on .bmp graphics

C 2 days 3hr Create “arena” - backgroung image(?) or black screen

D 4 days 5 hr Code player and player movements

E 4 days 6 hr Code single meteor/random locations/crosshairs

F 1 day 3 hr Code single stationary robo-fam member character – test to make sure it is working

G 4 days 5 hr Create game loop, attempt with one fam member

H 2 days 4hrs Create additional family robots and attempt

I 1 days 3 hrs Create different types of meteors/crosshairs and attempt

J 2 days 4 hrs Create different robo-abilities

K 2 days 3 hrs Polish game

A needs: feeds: BCDEFGHIJK

B needs: A

C needs: A, possibly B

D needs: A

E needs: A,B

F needs: A, B, D

G needs: A, B, C, D, E, F

H needs: A, B, C, D, E, F, G

I needs: A,B,C,D,E,F,G,H

J needs: A,B,C,D,E,F,G,H,I

K needs: All of the above